## Defects on Feb-18-21
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 8 | 8 | 5 | 21
Fixed |  | 4 | 4 | 5 | 13
Closed
Total | 0 | 12 | 12 | 10 | 34
ID | Severity | Title | Description | Status | Test Plan ID | Testing Status/Comments
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Open |  | Fixed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Open |  | Reopen
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Fixed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Fixed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Fixed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Fixed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Open
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | New |  | Fixed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Fixed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Open
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Open
12 | Medium | In Excel file, Performance Columns name should be as shown below, |  | Reopen |  | Reopen
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Fixed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Fixed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Reopen |  | Reopen
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Open |  | Fixed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Open
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Fixed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | New |  | Fixed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Fixed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Fixed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Fixed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Open
24 | Low | Excel file should be in below format, |  | Reopen |  | Reopen
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Fixed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Fixed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | New |  | Fixed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | New |  | Reopen
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | New |  | Reopen
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | New |  | Fixed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | New |  | Fixed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | New |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | New |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | New |  | Fixed

## Defects on Feb-24-21
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 2 | 1 | 2 | 5
Fixed | 2 | 16 | 13 | 14 | 45
Closed
Total | 2 | 18 | 14 | 16 | 50
ID | Severity | Title | Description | Status | Comments | Testing Comments
44 | High | If Only “Read Intensive” workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state If Only "VRO" workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state | Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | Reopen | Issue fixed for Write Intensive and VRO | Reopened
47 | High | Selected interfaces option, SSDs results are not displayed | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, SSDs results are displayed, | New
50 | Medium | SSDs Result number is mismatching in the Export Excel/CSV, Whening comparing with Result page |  | New |  | Fixed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Fixed | Old data is showing now | Fixed
49 | Low | In SSD Single File, Excel file download, Values are not showing | Random Read Average Latency uSec(4KiB,Q=1) Random Write Average Latency uSec (4KiB,Q=1) MAX Random Read IOPS (4KiB) Max Random Read IOPS (4KiB) Normalaized Max Random Write IOPS (4KiB) Normalaized For the above columns values are not showing | Open |  | Fixed
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Fixed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | Fixed
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Fixed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Fixed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Fixed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Fixed
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | Fixed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Fixed
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Fixed
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Fixed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Fixed
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Fixed
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Fixed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | Fixed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Fixed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Fixed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Fixed
24 | Low | Excel file should be in below format, |  | Fixed
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Fixed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Fixed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | Fixed
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | Fixed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | Fixed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | Fixed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Fixed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Fixed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Fixed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Fixed
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | Fixed
40 | Low | In Result Page, In the Server Type list, “Grok” Server type should be removed. |  | Fixed
37 | Medium | If Only “Read Intensive” workload is selected, then In Result Page Capacity should be 15.36 TB should be shown, Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | If “Select All/I Don’t Know Yet” option is selected in Server Type Page | Fixed
38 | Critical | Unable to Proceed further, if “Select All/I Don’t Know Yet” Option is selected in the Server Type Page for VRO, Read Intensive and Write Intensive workload (For Single or Multiple workloads) |  | Fixed
39 | Critical | When SSD results become zero, By Sliding Endurance/4K Max Random Read IOPS/4K Q16 Random Read IOPS/4K Q16 Random Write IOPS/4K Max Random Write IOPS/Max Power/Capacity to Min Point. Then Unable to go back to Max point. And other options in Result page is not working. | 1) Select the Single Workload, Click on Next Button, In Workload and SSD Page 2) Select the Server Type, Server Model and Capacity, Click on Next Button, in Server Type, Interface, Form Factor and Best Availability Page, 3) In Result Page, SSDs are displayed, then slide any Slider to Minimum point | Fixed
35 | High | Though options are not selected then also Next Button is enabled. | •Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. •Click Next Button in SSD page, •In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. •In SSD Type Click on Next Button, then Server Type Page, Next Button is enabled. | Fixed
36 | High | Without selecting Server type and Server Model, can be reached to the result page and SSDs are displayed. | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. d.In SSD Type Click on Next Button, then Server Type Page, Click Next Button, e.In Remaining Pages click Next Button. | Fixed
43 | High | In Server Type page, Next Button is enabled though options are not selected | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Click on “Select All/I Don’t Know Yet” then Click Next Button d. In Interface Page, Click on Back Button, Then in Server type page, Selected Options are not seen and Next Button is enabled | Fixed
46 | High | Changed values in Capacity drop down, will not shown in the result page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" then click "Next" Button. d. In the interface page, click "Back" Button, e. In Server type Page, Change the Capacity Value and Click on "Next" button in remaining pages f. In Result page, Latest selected Capacity will not be seen | Fixed
12 | Medium | In Excel file, Performance Columns name should be as shown, please refer to Issue No.6 |  | Fixed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Fixed
45 | Low | In Export CSV file, In "AC"cloumn - add "Random Read IOPS (4KiB,Q=16)"and Column heading needs to change in "AE" Column MAX Random Read IOPS (4KiB) and in "AB" Column it should be like this Random Write Average Latency uSec (4KiB,Q=1) |  | Fixed
42 | Low | Special Character need to remove for this SKU ID in DB-> P18430-B21. |  | Fixed
41 | Low | In Server type, Interface Type Alert should have Same font as below in the alert message, |  | Fixed
48 | Low | In Single Excel file download, Performance Columns need to change, same as the Export Excelsheet |  | Fixed

## Defects on Feb-26-21
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 4 | 1 | 0 | 5
Fixed | 2 | 16 | 13 | 16 | 47
Closed
Total | 2 | 20 | 14 | 16 | 52
ID | Severity | Title | Description | Status | Comments
44 | High | If Only “Read Intensive” workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state If Only "VRO" workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state | Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | Reopen | Issue fixed for Write Intensive and VRO
47 | High | Selected interfaces option, SSDs results are not displayed | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, SSDs results are displayed, | New
50 | Medium | SSDs Result number is mismatching in the Export Excel/CSV, Whening comparing with Result page |  | Partically Fixed | Export Excel is working fine
51 | High | SSDs results number are changing after downloading excel file, | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, "6"SSDs results are displayed, f. Then Click on Export Excel, File will be downloaded, g. Click on Non-Mainstream or Mainstream then SSDs numbers are changed | New
52 | High | SSDs Results are not there, then reaching to result page, it should block in Server type page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 300 Series" and Server Model as "DL325 Gen10 plus" and Select the Capacity as "900 to 1000 GB" d. Then Click Next in remaining pages e. In Result page, "0"SSDs results are displayed. Similarly it for same "0"SSDs results are displayed, for HPE Apollo Systems, for all Server models with the Capacity range is 900 GB to 1000 GB. | New
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Fixed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | Fixed
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Fixed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Fixed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Fixed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Fixed
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | Fixed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Fixed
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Fixed
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Fixed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Fixed
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Fixed
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Fixed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | Fixed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Fixed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Fixed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Fixed
24 | Low | Excel file should be in below format, |  | Fixed
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Fixed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Fixed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | Fixed
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | Fixed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | Fixed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | Fixed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Fixed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Fixed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Fixed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Fixed
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | Fixed
40 | Low | In Result Page, In the Server Type list, “Grok” Server type should be removed. |  | Fixed
37 | Medium | If Only “Read Intensive” workload is selected, then In Result Page Capacity should be 15.36 TB should be shown, Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | If “Select All/I Don’t Know Yet” option is selected in Server Type Page | Fixed
38 | Critical | Unable to Proceed further, if “Select All/I Don’t Know Yet” Option is selected in the Server Type Page for VRO, Read Intensive and Write Intensive workload (For Single or Multiple workloads) |  | Fixed
39 | Critical | When SSD results become zero, By Sliding Endurance/4K Max Random Read IOPS/4K Q16 Random Read IOPS/4K Q16 Random Write IOPS/4K Max Random Write IOPS/Max Power/Capacity to Min Point. Then Unable to go back to Max point. And other options in Result page is not working. | 1) Select the Single Workload, Click on Next Button, In Workload and SSD Page 2) Select the Server Type, Server Model and Capacity, Click on Next Button, in Server Type, Interface, Form Factor and Best Availability Page, 3) In Result Page, SSDs are displayed, then slide any Slider to Minimum point | Fixed
35 | High | Though options are not selected then also Next Button is enabled. | •Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. •Click Next Button in SSD page, •In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. •In SSD Type Click on Next Button, then Server Type Page, Next Button is enabled. | Fixed
36 | High | Without selecting Server type and Server Model, can be reached to the result page and SSDs are displayed. | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. d.In SSD Type Click on Next Button, then Server Type Page, Click Next Button, e.In Remaining Pages click Next Button. | Fixed
43 | High | In Server Type page, Next Button is enabled though options are not selected | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Click on “Select All/I Don’t Know Yet” then Click Next Button d. In Interface Page, Click on Back Button, Then in Server type page, Selected Options are not seen and Next Button is enabled | Fixed
46 | High | Changed values in Capacity drop down, will not shown in the result page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" then click "Next" Button. d. In the interface page, click "Back" Button, e. In Server type Page, Change the Capacity Value and Click on "Next" button in remaining pages f. In Result page, Latest selected Capacity will not be seen | Fixed
12 | Medium | In Excel file, Performance Columns name should be as shown, please refer to Issue No.6 |  | Fixed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Fixed
45 | Low | In Export CSV file, In "AC"cloumn - add "Random Read IOPS (4KiB,Q=16)"and Column heading needs to change in "AE" Column MAX Random Read IOPS (4KiB) and in "AB" Column it should be like this Random Write Average Latency uSec (4KiB,Q=1) |  | Fixed
42 | Low | Special Character need to remove for this SKU ID in DB-> P18430-B21. |  | Fixed
41 | Low | In Server type, Interface Type Alert should have Same font as below in the alert message, |  | Fixed
48 | Low | In Single Excel file download, Performance Columns need to change, same as the Export Excelsheet |  | Fixed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Fixed
49 | Low | In SSD Single File, Excel file download, Values are not showing | Random Read Average Latency uSec(4KiB,Q=1) Random Write Average Latency uSec (4KiB,Q=1) MAX Random Read IOPS (4KiB) Max Random Read IOPS (4KiB) Normalaized Max Random Write IOPS (4KiB) Normalaized For the above columns values are not showing | Fixed

## Defect on Mar-2nd-21
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 3 | 1 | 0 | 4
Fixed | 2 | 19 | 14 | 16 | 51
Closed
Total | 2 | 22 | 15 | 16 | 55
ID | Severity | Title | Description | Status | Comments
44 | High | If Only “Read Intensive” workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state If Only "VRO" workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state | Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | Reopen
54 | High | In Result Page, Capacity Slider is not functioning. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider, Slide the Maximum point to Min Point. | New
55 | High | In Result Page, when Uncheck the SSD Workload, SSDs are not Showing. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed, d) In SSD Workload, Uncheck the selected Workload, then SSDs result should be displayed. But now this message is displayed "There are no results based on your selection. Please select different attributes or start over." | New
53 | Medium | In Result Page, Initial Capacity Value is not showing in Capacity Slider, | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, Selected Initial Value is not shown in the Capacity Slider | New
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Fixed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | Fixed
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Fixed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Fixed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Fixed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Fixed
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | Fixed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Fixed
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Fixed
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Fixed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Fixed
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Fixed
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Fixed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | Fixed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Fixed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Fixed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Fixed
24 | Low | Excel file should be in below format, |  | Fixed
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Fixed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Fixed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | Fixed
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | Fixed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | Fixed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | Fixed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Fixed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Fixed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Fixed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Fixed
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | Fixed
40 | Low | In Result Page, In the Server Type list, “Grok” Server type should be removed. |  | Fixed
37 | Medium | If Only “Read Intensive” workload is selected, then In Result Page Capacity should be 15.36 TB should be shown, Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | If “Select All/I Don’t Know Yet” option is selected in Server Type Page | Fixed
38 | Critical | Unable to Proceed further, if “Select All/I Don’t Know Yet” Option is selected in the Server Type Page for VRO, Read Intensive and Write Intensive workload (For Single or Multiple workloads) |  | Fixed
39 | Critical | When SSD results become zero, By Sliding Endurance/4K Max Random Read IOPS/4K Q16 Random Read IOPS/4K Q16 Random Write IOPS/4K Max Random Write IOPS/Max Power/Capacity to Min Point. Then Unable to go back to Max point. And other options in Result page is not working. | 1) Select the Single Workload, Click on Next Button, In Workload and SSD Page 2) Select the Server Type, Server Model and Capacity, Click on Next Button, in Server Type, Interface, Form Factor and Best Availability Page, 3) In Result Page, SSDs are displayed, then slide any Slider to Minimum point | Fixed
35 | High | Though options are not selected then also Next Button is enabled. | •Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. •Click Next Button in SSD page, •In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. •In SSD Type Click on Next Button, then Server Type Page, Next Button is enabled. | Fixed
36 | High | Without selecting Server type and Server Model, can be reached to the result page and SSDs are displayed. | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. d.In SSD Type Click on Next Button, then Server Type Page, Click Next Button, e.In Remaining Pages click Next Button. | Fixed
43 | High | In Server Type page, Next Button is enabled though options are not selected | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Click on “Select All/I Don’t Know Yet” then Click Next Button d. In Interface Page, Click on Back Button, Then in Server type page, Selected Options are not seen and Next Button is enabled | Fixed
46 | High | Changed values in Capacity drop down, will not shown in the result page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" then click "Next" Button. d. In the interface page, click "Back" Button, e. In Server type Page, Change the Capacity Value and Click on "Next" button in remaining pages f. In Result page, Latest selected Capacity will not be seen | Fixed
12 | Medium | In Excel file, Performance Columns name should be as shown, please refer to Issue No.6 |  | Fixed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Fixed
45 | Low | In Export CSV file, In "AC"cloumn - add "Random Read IOPS (4KiB,Q=16)"and Column heading needs to change in "AE" Column MAX Random Read IOPS (4KiB) and in "AB" Column it should be like this Random Write Average Latency uSec (4KiB,Q=1) |  | Fixed
42 | Low | Special Character need to remove for this SKU ID in DB-> P18430-B21. |  | Fixed
41 | Low | In Server type, Interface Type Alert should have Same font as below in the alert message, |  | Fixed
48 | Low | In Single Excel file download, Performance Columns need to change, same as the Export Excelsheet |  | Fixed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Fixed
49 | Low | In SSD Single File, Excel file download, Values are not showing | Random Read Average Latency uSec(4KiB,Q=1) Random Write Average Latency uSec (4KiB,Q=1) MAX Random Read IOPS (4KiB) Max Random Read IOPS (4KiB) Normalaized Max Random Write IOPS (4KiB) Normalaized For the above columns values are not showing | Fixed
47 | High | Selected interfaces option, SSDs results are not displayed | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, SSDs results are displayed, | Fixed
50 | Medium | SSDs Result number is mismatching in the Export Excel/CSV, Whening comparing with Result page |  | Fixed | Export Excel is working fine
51 | High | SSDs results number are changing after downloading excel file, | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, "6"SSDs results are displayed, f. Then Click on Export Excel, File will be downloaded, g. Click on Non-Mainstream or Mainstream then SSDs numbers are changed | Fixed
52 | High | SSDs Results are not there, then reaching to result page, it should block in Server type page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 300 Series" and Server Model as "DL325 Gen10 plus" and Select the Capacity as "900 to 1000 GB" d. Then Click Next in remaining pages e. In Result page, "0"SSDs results are displayed. Similarly it for same "0"SSDs results are displayed, for HPE Apollo Systems, for all Server models with the Capacity range is 900 GB to 1000 GB. | Fixed

## Defect on Mar-3rd-21
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 4 | 1 | 0 | 5
Fixed | 2 | 22 | 15 | 16 | 55
Closed
Total | 2 | 26 | 16 | 16 | 60
ID | Severity | Title | Description | Status | Comments
56 | High | In Result page, In Capacity Slider value changes on click on SSD Workload | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider it shows 900GB to 1000GB, Refer Fig (A) d) Click on "Read Intensive" Check Box in the SSD Workload Refer Fig (B) e) Then Uncheck Selected workload from the configuration f) In the Capacity Slider, Slider value changes to 0 GB to 15.23 TB | New
57 | High | In Result page, Capacity Slider value is zero, then also SSDs Results are showing. | a) Select VRO/Read Intensive/Write Intensive workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed. d) In Capacity Slider, Slider Max Point to Min Point, then Capacity Value will be zero. | New
58 | High | ) In Result page, Selected value is not showing in the Capacity Slider, Selected Value :- 1.5 TB to 1.6 TB from Drop Down in Server Type page, In Capacity Slider Showing :- 1500 (GB) to 1600 (TB) If we Slider the Slider, then changes to 1.5 (GB) to 1.6 (TB) | a)Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "1.5-1.6TB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider it shows 1500 GB to 1600 TB. | New
59 | High | In Result page, Capacity Slider Value changes, on selecting the SSD Workloads | a) In Home Page, click on "I Know What I Need" b) In Result Page, then 210 SSDs results are displayed. c) In SSD Workload Section, Deselect the Workload such as "Very Read Optimized" , "Read Intensive", "Mixed Use" and "Write Intensive". d) Then In SSD Workload Section, Select the any one workload such as "Very Read Optimized" /"Write Intensive"/ "Read Intensive" /"Mixed Use" e) Then Selected Workload value will not be seen in the Capacity Slider | New
60 | Medium | In Server type Page, Selected Capacity Range will not retained on Click Back in the Interface Page. | a)Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "1.5-1.6TB" Then Click Next Button c) Then in Interface page, Click Back Button, d) Then in Server type page, Capacity Range Tab shows Empty. | New
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Fixed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | Fixed
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Fixed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Fixed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Fixed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Fixed
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | Fixed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Fixed
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Fixed
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Fixed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Fixed
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Fixed
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Fixed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | Fixed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Fixed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Fixed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Fixed
24 | Low | Excel file should be in below format, |  | Fixed
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Fixed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Fixed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | Fixed
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | Fixed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | Fixed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | Fixed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Fixed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Fixed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Fixed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Fixed
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | Fixed
40 | Low | In Result Page, In the Server Type list, “Grok” Server type should be removed. |  | Fixed
37 | Medium | If Only “Read Intensive” workload is selected, then In Result Page Capacity should be 15.36 TB should be shown, Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | If “Select All/I Don’t Know Yet” option is selected in Server Type Page | Fixed
38 | Critical | Unable to Proceed further, if “Select All/I Don’t Know Yet” Option is selected in the Server Type Page for VRO, Read Intensive and Write Intensive workload (For Single or Multiple workloads) |  | Fixed
39 | Critical | When SSD results become zero, By Sliding Endurance/4K Max Random Read IOPS/4K Q16 Random Read IOPS/4K Q16 Random Write IOPS/4K Max Random Write IOPS/Max Power/Capacity to Min Point. Then Unable to go back to Max point. And other options in Result page is not working. | 1) Select the Single Workload, Click on Next Button, In Workload and SSD Page 2) Select the Server Type, Server Model and Capacity, Click on Next Button, in Server Type, Interface, Form Factor and Best Availability Page, 3) In Result Page, SSDs are displayed, then slide any Slider to Minimum point | Fixed
35 | High | Though options are not selected then also Next Button is enabled. | •Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. •Click Next Button in SSD page, •In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. •In SSD Type Click on Next Button, then Server Type Page, Next Button is enabled. | Fixed
36 | High | Without selecting Server type and Server Model, can be reached to the result page and SSDs are displayed. | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. d.In SSD Type Click on Next Button, then Server Type Page, Click Next Button, e.In Remaining Pages click Next Button. | Fixed
43 | High | In Server Type page, Next Button is enabled though options are not selected | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Click on “Select All/I Don’t Know Yet” then Click Next Button d. In Interface Page, Click on Back Button, Then in Server type page, Selected Options are not seen and Next Button is enabled | Fixed
46 | High | Changed values in Capacity drop down, will not shown in the result page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" then click "Next" Button. d. In the interface page, click "Back" Button, e. In Server type Page, Change the Capacity Value and Click on "Next" button in remaining pages f. In Result page, Latest selected Capacity will not be seen | Fixed
12 | Medium | In Excel file, Performance Columns name should be as shown, please refer to Issue No.6 |  | Fixed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Fixed
45 | Low | In Export CSV file, In "AC"cloumn - add "Random Read IOPS (4KiB,Q=16)"and Column heading needs to change in "AE" Column MAX Random Read IOPS (4KiB) and in "AB" Column it should be like this Random Write Average Latency uSec (4KiB,Q=1) |  | Fixed
42 | Low | Special Character need to remove for this SKU ID in DB-> P18430-B21. |  | Fixed
41 | Low | In Server type, Interface Type Alert should have Same font as below in the alert message, |  | Fixed
48 | Low | In Single Excel file download, Performance Columns need to change, same as the Export Excelsheet |  | Fixed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Fixed
49 | Low | In SSD Single File, Excel file download, Values are not showing | Random Read Average Latency uSec(4KiB,Q=1) Random Write Average Latency uSec (4KiB,Q=1) MAX Random Read IOPS (4KiB) Max Random Read IOPS (4KiB) Normalaized Max Random Write IOPS (4KiB) Normalaized For the above columns values are not showing | Fixed
47 | High | Selected interfaces option, SSDs results are not displayed | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, SSDs results are displayed, | Fixed
50 | Medium | SSDs Result number is mismatching in the Export Excel/CSV, Whening comparing with Result page |  | Fixed | Export Excel is working fine
51 | High | SSDs results number are changing after downloading excel file, | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, "6"SSDs results are displayed, f. Then Click on Export Excel, File will be downloaded, g. Click on Non-Mainstream or Mainstream then SSDs numbers are changed | Fixed
52 | High | SSDs Results are not there, then reaching to result page, it should block in Server type page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 300 Series" and Server Model as "DL325 Gen10 plus" and Select the Capacity as "900 to 1000 GB" d. Then Click Next in remaining pages e. In Result page, "0"SSDs results are displayed. Similarly it for same "0"SSDs results are displayed, for HPE Apollo Systems, for all Server models with the Capacity range is 900 GB to 1000 GB. | Fixed
44 | High | If Only “Read Intensive” workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state If Only "VRO" workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state | Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | Fixed
54 | High | In Result Page, Capacity Slider is not functioning. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider, Slide the Maximum point to Min Point. | Fixed
55 | High | In Result Page, when Uncheck the SSD Workload, SSDs are not Showing. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed, d) In SSD Workload, Uncheck the selected Workload, then SSDs result should be displayed. But now this message is displayed "There are no results based on your selection. Please select different attributes or start over." | Fixed
53 | Medium | In Result Page, Initial Capacity Value is not showing in Capacity Slider, | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, Selected Initial Value is not shown in the Capacity Slider | Fixed

## Status on 4-3-21
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 0 | 0 | 0 | 0
Fixed | 0 | 0 | 0 | 0 | 0
Closed | 2 | 26 | 16 | 16 | 60
Total | 2 | 26 | 16 | 16 | 60
ID | Severity | Title | Description | Status | Comments
56 | High | In Result page, In Capacity Slider value changes on click on SSD Workload | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider it shows 900GB to 1000GB, Refer Fig (A) d) Click on "Read Intensive" Check Box in the SSD Workload Refer Fig (B) e) Then Uncheck Selected workload from the configuration f) In the Capacity Slider, Slider value changes to 0 GB to 15.23 TB | Closed
57 | High | In Result page, Capacity Slider value is zero, then also SSDs Results are showing. | a) Select VRO/Read Intensive/Write Intensive workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed. d) In Capacity Slider, Slider Max Point to Min Point, then Capacity Value will be zero. | Closed
58 | High | ) In Result page, Selected value is not showing in the Capacity Slider, Selected Value :- 1.5 TB to 1.6 TB from Drop Down in Server Type page, In Capacity Slider Showing :- 1500 (GB) to 1600 (TB) If we Slider the Slider, then changes to 1.5 (GB) to 1.6 (TB) | a)Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "1.5-1.6TB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider it shows 1500 GB to 1600 TB. | Closed
59 | High | In Result page, Capacity Slider Value changes, on selecting the SSD Workloads | a) In Home Page, click on "I Know What I Need" b) In Result Page, then 210 SSDs results are displayed. c) In SSD Workload Section, Deselect the Workload such as "Very Read Optimized" , "Read Intensive", "Mixed Use" and "Write Intensive". d) Then In SSD Workload Section, Select the any one workload such as "Very Read Optimized" /"Write Intensive"/ "Read Intensive" /"Mixed Use" e) Then Selected Workload value will not be seen in the Capacity Slider | Closed
60 | Medium | In Server type Page, Selected Capacity Range will not retained on Click Back in the Interface Page. | a)Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "1.5-1.6TB" Then Click Next Button c) Then in Interface page, Click Back Button, d) Then in Server type page, Capacity Range Tab shows Empty. | Closed
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Closed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | Closed
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Closed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Closed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Closed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Closed
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | Closed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Closed
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Closed
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Closed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Closed
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Closed
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Closed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | Closed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Closed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Closed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Closed
24 | Low | Excel file should be in below format, |  | Closed
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Closed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Closed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | Closed
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | Closed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | Closed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | Closed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Closed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Closed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Closed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Closed
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | Closed
40 | Low | In Result Page, In the Server Type list, “Grok” Server type should be removed. |  | Closed
37 | Medium | If Only “Read Intensive” workload is selected, then In Result Page Capacity should be 15.36 TB should be shown, Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | If “Select All/I Don’t Know Yet” option is selected in Server Type Page | Closed
38 | Critical | Unable to Proceed further, if “Select All/I Don’t Know Yet” Option is selected in the Server Type Page for VRO, Read Intensive and Write Intensive workload (For Single or Multiple workloads) |  | Closed
39 | Critical | When SSD results become zero, By Sliding Endurance/4K Max Random Read IOPS/4K Q16 Random Read IOPS/4K Q16 Random Write IOPS/4K Max Random Write IOPS/Max Power/Capacity to Min Point. Then Unable to go back to Max point. And other options in Result page is not working. | 1) Select the Single Workload, Click on Next Button, In Workload and SSD Page 2) Select the Server Type, Server Model and Capacity, Click on Next Button, in Server Type, Interface, Form Factor and Best Availability Page, 3) In Result Page, SSDs are displayed, then slide any Slider to Minimum point | Closed
35 | High | Though options are not selected then also Next Button is enabled. | •Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. •Click Next Button in SSD page, •In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. •In SSD Type Click on Next Button, then Server Type Page, Next Button is enabled. | Closed
36 | High | Without selecting Server type and Server Model, can be reached to the result page and SSDs are displayed. | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. d.In SSD Type Click on Next Button, then Server Type Page, Click Next Button, e.In Remaining Pages click Next Button. | Closed
43 | High | In Server Type page, Next Button is enabled though options are not selected | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Click on “Select All/I Don’t Know Yet” then Click Next Button d. In Interface Page, Click on Back Button, Then in Server type page, Selected Options are not seen and Next Button is enabled | Closed
46 | High | Changed values in Capacity drop down, will not shown in the result page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" then click "Next" Button. d. In the interface page, click "Back" Button, e. In Server type Page, Change the Capacity Value and Click on "Next" button in remaining pages f. In Result page, Latest selected Capacity will not be seen | Closed
12 | Medium | In Excel file, Performance Columns name should be as shown, please refer to Issue No.6 |  | Closed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Closed
45 | Low | In Export CSV file, In "AC"cloumn - add "Random Read IOPS (4KiB,Q=16)"and Column heading needs to change in "AE" Column MAX Random Read IOPS (4KiB) and in "AB" Column it should be like this Random Write Average Latency uSec (4KiB,Q=1) |  | Closed
42 | Low | Special Character need to remove for this SKU ID in DB-> P18430-B21. |  | Closed
41 | Low | In Server type, Interface Type Alert should have Same font as below in the alert message, |  | Closed
48 | Low | In Single Excel file download, Performance Columns need to change, same as the Export Excelsheet |  | Closed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Closed
49 | Low | In SSD Single File, Excel file download, Values are not showing | Random Read Average Latency uSec(4KiB,Q=1) Random Write Average Latency uSec (4KiB,Q=1) MAX Random Read IOPS (4KiB) Max Random Read IOPS (4KiB) Normalaized Max Random Write IOPS (4KiB) Normalaized For the above columns values are not showing | Closed
47 | High | Selected interfaces option, SSDs results are not displayed | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, SSDs results are displayed, | Closed
50 | Medium | SSDs Result number is mismatching in the Export Excel/CSV, Whening comparing with Result page |  | Closed | Export Excel is working fine
51 | High | SSDs results number are changing after downloading excel file, | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, "6"SSDs results are displayed, f. Then Click on Export Excel, File will be downloaded, g. Click on Non-Mainstream or Mainstream then SSDs numbers are changed | Closed
52 | High | SSDs Results are not there, then reaching to result page, it should block in Server type page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 300 Series" and Server Model as "DL325 Gen10 plus" and Select the Capacity as "900 to 1000 GB" d. Then Click Next in remaining pages e. In Result page, "0"SSDs results are displayed. Similarly it for same "0"SSDs results are displayed, for HPE Apollo Systems, for all Server models with the Capacity range is 900 GB to 1000 GB. | Closed
44 | High | If Only “Read Intensive” workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state If Only "VRO" workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state | Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | Closed
54 | High | In Result Page, Capacity Slider is not functioning. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider, Slide the Maximum point to Min Point. | Closed
55 | High | In Result Page, when Uncheck the SSD Workload, SSDs are not Showing. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed, d) In SSD Workload, Uncheck the selected Workload, then SSDs result should be displayed. But now this message is displayed "There are no results based on your selection. Please select different attributes or start over." | Closed
53 | Medium | In Result Page, Initial Capacity Value is not showing in Capacity Slider, | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, Selected Initial Value is not shown in the Capacity Slider | Closed

## Stage Issues
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen |  | 0 | 0 | 0 | 0
Fixed | 0 | 0 | 0 | 0 | 0
Closed | 2 | 26 | 16 | 16 | 60
Total | 2 | 26 | 16 | 16 | 60
ID | Severity | Title | Description | Status | Comments
56 | High | In Result page, In Capacity Slider value changes on click on SSD Workload | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider it shows 900GB to 1000GB, Refer Fig (A) d) Click on "Read Intensive" Check Box in the SSD Workload Refer Fig (B) e) Then Uncheck Selected workload from the configuration f) In the Capacity Slider, Slider value changes to 0 GB to 15.23 TB | Closed
57 | High | In Result page, Capacity Slider value is zero, then also SSDs Results are showing. | a) Select VRO/Read Intensive/Write Intensive workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed. d) In Capacity Slider, Slider Max Point to Min Point, then Capacity Value will be zero. | Closed
58 | High | ) In Result page, Selected value is not showing in the Capacity Slider, Selected Value :- 1.5 TB to 1.6 TB from Drop Down in Server Type page, In Capacity Slider Showing :- 1500 (GB) to 1600 (TB) If we Slider the Slider, then changes to 1.5 (GB) to 1.6 (TB) | a)Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "1.5-1.6TB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider it shows 1500 GB to 1600 TB. | Closed
59 | High | In Result page, Capacity Slider Value changes, on selecting the SSD Workloads | a) In Home Page, click on "I Know What I Need" b) In Result Page, then 210 SSDs results are displayed. c) In SSD Workload Section, Deselect the Workload such as "Very Read Optimized" , "Read Intensive", "Mixed Use" and "Write Intensive". d) Then In SSD Workload Section, Select the any one workload such as "Very Read Optimized" /"Write Intensive"/ "Read Intensive" /"Mixed Use" e) Then Selected Workload value will not be seen in the Capacity Slider | Closed
60 | Medium | In Server type Page, Selected Capacity Range will not retained on Click Back in the Interface Page. | a)Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "1.5-1.6TB" Then Click Next Button c) Then in Interface page, Click Back Button, d) Then in Server type page, Capacity Range Tab shows Empty. | Closed
1 | High | In Result page, SSDs results are displayed though options are not selected. |  | Closed
28 | Low | In Interface Page, though single option is selected, "Select All / I Don't Know Yet" option should not be selected |  | Closed
3 | High | In Result Page, though “Read Intensive/Write Intensive/Mixed Use” option is selected, but all SSD’s results are displayed with Mixed and Write. |  | Closed
4 | High | In Result Page, click on “Select All/Uncheck All”, then different set of SSDs are displayed. Before Clicking on “Select All/Uncheck All | After Click on “Select All/Uncheck All” | Closed
5 | High | In Result Page, SSDs results are not displayed based on the SSD Workload, Interface, Form Factor filter |  | Closed
6 | High | In Result Page, though SSDs results are available, “0 – SSDs meet your requirements” message is displayed, | a. In result page, In search for invalid SKU in “Search Tab” b. In search Tab, enter the invalid SKU number, c. Then click on Search icon, then Correct error Message is displayed, d. Erase the invalid SKU Number in search tab, then, “0 – SSDs meet your requirements” message is displayed. | Closed
8 | High | In Result Page though options are not selected in workload page, In SSD Workload though options are selected. |  | Closed
9 | Medium | In Server Type page and Result page, Server Model List is displayed not based on selected Server type. |  | Closed
11 | Medium | In Result page, options are unchecked mode, can click the check box. |  | Closed
13 | Medium | In Interface page, “Select All / I Do not Know Yet” option should be unchecked mode, when click on Interface options such as “SAS, Value SAS.” |  | Closed
14 | Medium | In Server Type page, without selecting the server Type, Next Button is enabled |  | Closed
16 | Medium | In Form Factor Page, though options are not showing then also Next button is showing. |  | Closed
18 | Medium | In Result Page, Mainstream and Non – Mainstream label is not showing in the SSD’s results. |  | Closed
19 | Medium | In Interface Page, Deselected Options are selected, on click Back in Form Factor Page |  | Closed
20 | Low | In Server Type page, Server Model Tab is enabled before selecting the Server Type. - |  | Closed
21 | Low | Selected Capacity is not shown in the Capacity Tab, on click on “Back” Button in Interface Page, |  | Closed
22 | Low | In Result Page, Semicolon are showing twice, in show more option |  | Closed
24 | Low | Excel file should be in below format, |  | Closed
25 | Low | In Interface Page, Selected options should be in highlighted State. |  | Closed
26 | Low | In Interface page, “Select All / I Don’t Know Yet” option is not selected | a.In Interface Page, deselect the selected checkbox. b.Then “Select All / I Don’t Know yet” option will be unchecked mode. c.Then Click on Interface options such as “SAS, Value SAS, SATA, SATA VRO, NVMe Mainstream and NVMe High Performance, d.Then “Select All / I Don’t Know yet” option should be selected. But it is not selected | Closed
27 | Low | Select Capacity Label should be displayed in Capacity Tab, in Server Type page |  | Closed
30 | High | In Server Type Page, Unable to Change the Server Model from the drop down, | In Server Type Page, Unable to Change the Server Model from the drop down, a) To Change Server Model, we change the Server Type | Closed
31 | Medium | In Result Page, Server Model Tab shows empty, | a) Select the workload, Click Next b) Click on SSD Page C) In Server Type page, Select the Server Type, Server Model and Capacity and Click Next d) Click on "Back" Button, in Interface page, e) Change the Server model from the Drop, Then Click Next in all Pages | Closed
32 | High | For "Read Intensive/Mixed Use" Workload, Interface options are not supported in Interface Page, But in Result Page, Options are clickable for SAS, Value SAS, NVMe Mainstream and NVMe High Performance, |  | As per requirment is working
33 | High | For "VRO" Workload, Interface Option selected with "SATA VRO", In Result Page, SSDs results are displayed with SATA description. |  | As per requirment is working
34 | Low | Capacity Range Tab shows empty, On Click on Back Button in Interface Page, |  | Closed
2 | High | In Result Page, SSDs results are displayed more than capacity value showed in the Capacity Slider/Selected in the Capacity Drop Down in Server type page |  | Closed
7 | High | In Result page, Moving the slider from Max to Min, then SSDs results are not change. |  | Closed
15 | Medium | In Interface Page, though all options are not selected then also “Select All / I Don’t Know Yet.” Option is selected | In Interface Page, Deselect the Options, then "Select All/I Don't Know Yet" option will be unchecked mode. Then Click Next Button, In Formfactor Page, Click Back Button. In the Interface Page, "Select All/I Don't Know Yet" is selected, though other all options are not selected | Closed
10 | Medium | For VRO Workloads, though Capacity is selected with “300 GB to 400 GB”, in the result page it shows “0TB to 1530TB.” |  | Closed
29 | High | Click Back Button in Interface Page, When One Option interface is available, then unable to Proceed further from the Server Type |  | Closed
40 | Low | In Result Page, In the Server Type list, “Grok” Server type should be removed. |  | Closed
37 | Medium | If Only “Read Intensive” workload is selected, then In Result Page Capacity should be 15.36 TB should be shown, Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | If “Select All/I Don’t Know Yet” option is selected in Server Type Page | Closed
38 | Critical | Unable to Proceed further, if “Select All/I Don’t Know Yet” Option is selected in the Server Type Page for VRO, Read Intensive and Write Intensive workload (For Single or Multiple workloads) |  | Closed
39 | Critical | When SSD results become zero, By Sliding Endurance/4K Max Random Read IOPS/4K Q16 Random Read IOPS/4K Q16 Random Write IOPS/4K Max Random Write IOPS/Max Power/Capacity to Min Point. Then Unable to go back to Max point. And other options in Result page is not working. | 1) Select the Single Workload, Click on Next Button, In Workload and SSD Page 2) Select the Server Type, Server Model and Capacity, Click on Next Button, in Server Type, Interface, Form Factor and Best Availability Page, 3) In Result Page, SSDs are displayed, then slide any Slider to Minimum point | Closed
35 | High | Though options are not selected then also Next Button is enabled. | •Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. •Click Next Button in SSD page, •In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. •In SSD Type Click on Next Button, then Server Type Page, Next Button is enabled. | Closed
36 | High | Without selecting Server type and Server Model, can be reached to the result page and SSDs are displayed. | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type Click on “Select All/I Don’t Know Yet” then click on Back Button. d.In SSD Type Click on Next Button, then Server Type Page, Click Next Button, e.In Remaining Pages click Next Button. | Closed
43 | High | In Server Type page, Next Button is enabled though options are not selected | a.Select VRO/Read/Write Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Click on “Select All/I Don’t Know Yet” then Click Next Button d. In Interface Page, Click on Back Button, Then in Server type page, Selected Options are not seen and Next Button is enabled | Closed
46 | High | Changed values in Capacity drop down, will not shown in the result page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" then click "Next" Button. d. In the interface page, click "Back" Button, e. In Server type Page, Change the Capacity Value and Click on "Next" button in remaining pages f. In Result page, Latest selected Capacity will not be seen | Closed
12 | Medium | In Excel file, Performance Columns name should be as shown, please refer to Issue No.6 |  | Closed
17 | Medium | In Result Page, In Capacity Slider it is showing 300TB to 400TB, in server type page selected capacity value is 300GB to 400GB. |  | Closed
45 | Low | In Export CSV file, In "AC"cloumn - add "Random Read IOPS (4KiB,Q=16)"and Column heading needs to change in "AE" Column MAX Random Read IOPS (4KiB) and in "AB" Column it should be like this Random Write Average Latency uSec (4KiB,Q=1) |  | Closed
42 | Low | Special Character need to remove for this SKU ID in DB-> P18430-B21. |  | Closed
41 | Low | In Server type, Interface Type Alert should have Same font as below in the alert message, |  | Closed
48 | Low | In Single Excel file download, Performance Columns need to change, same as the Export Excelsheet |  | Closed
23 | Low | In Workload Page, “To Learn More About Workloads Click Here” link is redirecting to Not Found page, |  | Closed
49 | Low | In SSD Single File, Excel file download, Values are not showing | Random Read Average Latency uSec(4KiB,Q=1) Random Write Average Latency uSec (4KiB,Q=1) MAX Random Read IOPS (4KiB) Max Random Read IOPS (4KiB) Normalaized Max Random Write IOPS (4KiB) Normalaized For the above columns values are not showing | Closed
47 | High | Selected interfaces option, SSDs results are not displayed | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, SSDs results are displayed, | Closed
50 | Medium | SSDs Result number is mismatching in the Export Excel/CSV, Whening comparing with Result page |  | Closed | Export Excel is working fine
51 | High | SSDs results number are changing after downloading excel file, | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 100 Series" and Server Model as "DL160 Gen10" and Select the Capacity as "400 to 500 GB" d. Then Click Next in remaining pages e. In Result page, "6"SSDs results are displayed, f. Then Click on Export Excel, File will be downloaded, g. Click on Non-Mainstream or Mainstream then SSDs numbers are changed | Closed
52 | High | SSDs Results are not there, then reaching to result page, it should block in Server type page | a.Select Read Workload, (Single or Multiple workloads) the Click on Next Button. b.Click Next Button in SSD page, c.In Server Type page, Select Server type as "HPE Proliant 300 Series" and Server Model as "DL325 Gen10 plus" and Select the Capacity as "900 to 1000 GB" d. Then Click Next in remaining pages e. In Result page, "0"SSDs results are displayed. Similarly it for same "0"SSDs results are displayed, for HPE Apollo Systems, for all Server models with the Capacity range is 900 GB to 1000 GB. | Closed
44 | High | If Only “Read Intensive” workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state If Only "VRO" workload is selected, then In Result Page, In Capacity Slider, 0TB to 15.36 TB it is in disabled state | Similarly, if applies to VRO: - 7.6 TB, For Mixed Use: - 12.8 TB and Write Intensive: - 3.2 TB, | Closed
54 | High | In Result Page, Capacity Slider is not functioning. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, In the Capacity Slider, Slide the Maximum point to Min Point. | Closed
55 | High | In Result Page, when Uncheck the SSD Workload, SSDs are not Showing. | a) Select VRO/Read Intensive/Write Intensive/Mixed Use workload as a single or Multiple , Then Click on Next Button b) In Server Type Page, click on "Select All/I Don't Know yet" Option , Then Click Next Button, and Click Next Button in remaining pages. c) In Result Page, SSDs are displayed, d) In SSD Workload, Uncheck the selected Workload, then SSDs result should be displayed. But now this message is displayed "There are no results based on your selection. Please select different attributes or start over." | Closed
53 | Medium | In Result Page, Initial Capacity Value is not showing in Capacity Slider, | a) Select VRO/Read Intensive/Write Intensive/Mixed Use, Workload as a Single or Multiple, The Click on Next Button, b) In Server Type Page, Select the Server Type, Server Model and Capacity value such as "900GB to 1000GB" Then Click Next Button and Click Next Button in remaining pages. c) In Result Page, Selected Initial Value is not shown in the Capacity Slider | Closed