## Features
Feature Set included for SSD Selector Release V1.0 (Release Date 08/21)
EPIC ID | EPIC | Story ID | Stories | V1 Release | Story Points | Effort in Hours | Start Date | End Date | FC Status | QA Status | Remarks | Dev Comments | QA Comments
E1 | UI/UX features set1
|  | S1 | S1 - Mainstream/ Non-Mainstream | yes | 13 | 32 | 2020-08-07 |  | Completed |  | 4 Open Issues | Completed at Localhost, need to check at stage
|  | S2 | S2 - For the user, provide an option to search SSD by server type, model | yes | 3 | 4 | 2020-03-01 | 2020-05-01 | Completed |  |  | Issued fixed Prashant need to check
|  | S3 | S3 - For the user, provide simplified UX experience with minimal clicks and reduced navigations | yes | 5 | 8 | 2020-03-01 | 2020-05-01 | Completed |  |  | Issued fixed Prashant need to check
|  | S4 | S4 - For the user, provde output of the tool to be exported in an Excel format | yes | 8 | 10 | 2020-03-01 | 2020-05-01 | Completed |  | PDF load takes long. Excel req from field first. | Started working on that
|  | S5 | S5 - For the user, provide visual representation of the output through graphical representation (tied to S7) | yes | 13 | 16 | 2020-03-01 | 2020-05-01 | At Risk |  | S5 is duplicate of S7
|  | S6 | S6 - Remove Recommended/Extended as that initiative is no longer being supported. | yes | 5 | 8 | 2020-03-01 | 2020-05-01 | Completed
|  | S7 | S7- Update the portfolio alignment slide to add our new swim lanes | yes |  |  | 2020-03-01 | 2020-05-01 | Completed |  | S5 is duplicate of S7
|  | S8 | S8 - Change the workload categories from 3 to 4 - Very Read Optimized (VRO) | yes |  |  | 2020-05-01 | 2020-06-30 | Completed
|  | S9 | S9 - Update the interfaces categories as well (add Value SAS, add three different sub segments of NVMe, etc.) | yes |  |  | 2020-03-01 | 2020-05-01 | Completed
|  | S10 | S10 - Remove Mezzanine Card from facets |  |  |  | 2020-03-01 | 2020-05-01 | Completed
E2 | Product features set1
|  | S11 | S11 - Implement all SSDs for DL385 Gen10 | yes | 5 |  |  |  | Completed | Completed |  |  | Once the Server is deployed at Stage with latest DB, I will start working on that
|  | S12 | S12 - Implement all SSDs for Synergy Gen10 | yes | 5 |  |  |  | Completed |  | Balamani to commit S12- S15 ASAP on 8/20
|  | S13 | S13 - Implement all SSDs from Quartz NPI Launch | yes | 21 |  |  |  | Completed
|  | S14 | S14 - Implment all SSDs from Kyanite NPI Launch | yes | 13 |  |  |  | Completed
|  | S15 | S15 - Implement all SSDs for Gen10 Plus Servers | yes |  |  |  |  | Completed
|  |  | MileStones |  | Date
|  |  | Functional Complete |  | 2020-08-14
|  |  | Beta Version |  | 2020-08-13 | 2020-08-17
|  |  | QA Complete & RC |  | 2020-08-19
|  |  | PRG Checkpoint |  | 2020-08-21
|  |  | Production Release |  | 2020-08-24
Notes
Above status color is an example but fill with actual status as of now
No code change allowed beyond 19-Aug except show stopper issues
Code & QA should have frozen before we enter into PRG checkpoint
E3 | Future Backlog |  | Backlog section is reserved for management. No edits allowed here.
|  | S16 | S16 - For the user, provde output of the tool to be exported in an PDF format
Enhancement
In Result page, After the Selecting the Server type, in the Server Model Tab, "Select Server Model" Label should be seen
In Result page, After selecting the Server type and Server Model, Result page should scroll down to SSDs Result View

## Test Plan Execution
ID | EPIC/Category | Title | Total Test Cases Planned | Total Test Cases Executed | Tests passed | Tests failed | Defects Summary | Blockers | QA Execution Status and Completion Date | Defect Verification Status | Overall QA Status & Sign-Off
1 | Feature | S1 - Mainstream/ Non-Mainstream | 8 | 8 | 8 | 0
2 | Feature | S2 - For the user, provide an option to search SSD by server type, model | 5 | 5 | 5 | 0 | Unable to see the results based on the Server Type and Model selected from the drop down. And unable to retrive the results. 5 Test Cases - SSDV1.1_50, SSDV1.1_51, SSDV1.1_81, SSDV1.1_082, SSDV1.1_83
3 | Feature | S3 - For the user, provide simplified UX experience with minimal clicks and reduced navigations | 26 | 26 | 26 | 0 | Unable to see the auto selected check box for options in the interface and Form factor page. 4 Test Cases - SSDV1.1_073, SSDV1.1_075, SSDV1.1_079, SSDV1.1_080
4 | Feature | S4 - For the user, provde output of the tool to be exported in a PDF format | 2 | 2 | 2
5 | Feature | S5 - For the user, provide visual representation of the output through graphical representation | 3 | 3 | 3 | 0
6 | Feature | S6 - Remove Recommended/Extended as that initiative is no longer being supported. | 1 | 1 | 1
7 | Feature | S7- Update the portfolio alignment slide to add our new swim lanes
8 | Feature | S8 - Change the workload categories from 3 to 4 - Very Read Optimized (VRO) | 6 | 6 | 6 | 0 | Validation is not happened for Check box in the "Select All/I don't Know" SSDV1.1_009, SSDV1.1_072,SSDV1.1_131 In the Server Type Page, Selected VRO Workload and Target server Type names are not displayed.
9 | Feature | S9 - Update the interfaces categories as well (add Value SAS, add three different sub segments of NVMe, etc.) | 14 | 14 | 14 | 0 | Options should be autoselected in the Interface and Form Factor page 2 Test Cases
10 | Feature | S10 - Remove Mezzanine Card from facets | 12 | 12 | 12 | 0 | Options should be autoselected in the Form Factor page 2Test Cases
11 | Product | S11 - Implement all SSDs for DL385 Gen10 | 6 | 6 | 6 | 0
12 | Product | S12 - Implement all SSDs for Synergy Gen10 | 6 | 6 | 6 | 0 | SSDV1.1_124,SSDV1.1_136 1.SSDs Results not coming properly based on the Server Type and Server Model for "HPE Synergy" and Synergy 660 Gen10. 2.In the SSDs click on Show More, In the Compatibility Server Part, Data base query is showing
13 | Product | S13 - Implement all SSDs from Quartz NPI Launch | 6 | 6 | 6 | 0 | SSDV1.1_141,SSDV1.1_142 1. SSDs Results not coming properly based on the Server Type and Server Model for "HPE Apollo Systems" and Apollo 2000 Gen10. 2.In the SSDs click on Show More, In the Compatibility Server Part, Data base query is showing
14 | Product | S14 - Implment all SSDs from Kyanite NPI Launch | 6 | 6 | 6 | 0 | SSDV1.1_147,SSDV1.1_148 1. SSDs Results not coming properly based on the Server Type and Server Model for "HPE Apollo Systems" and Apollo 4200 Gen10. 2.In the SSDs click on Show More, In the Compatibility Server Part, Data base query is showing
15 | Product | S15 - Implement all SSDs for Gen10 Plus Servers | 6 | 6 | 6 | 0 | SSDV1.1_153,SSDV1.1_154 1. SSDs Results not coming properly based on the Server Type and Server Model for "HPE ProLiant 300 Series" and DL385 Gen10 plus. 2.In the SSDs click on Show More, In the Compatibility Server Part, Data base query is showing
16 | Performance | Application performance testing | 10 | 10 | 10 | 0
17 | Scalability | Application scalability testing | 12 | 12 | 12 | 0 | Bug IDs :- 46 (3,4,5,6,7,8) Response Time and Throughput is not constant
18 | Intergration | Application Integration testing (including results) | 3 | 3 | 3 | 0 | 19,25,15 Bug ID: 24, Issue fixed but Tab functionality is disabled in that page. Bug ID : 26 , Issue Fixed, Now it redirects to Home Page Bug ID:- 32, Issue Fixed, it redirects to Home Page
19 | Browser Compactability Testing | Browser Compactability Testing | 44 | 44 | 44 | 0 | In Chrome and Microsoft Edge Browser, SSD Selector tool is working fine. In Internet Explorer, unable to proceed from server type page
20 | Security | Application security testing | 4 | 4 | 4 | 0 | 1. Copy and Paste results page URL in the another browser. "https://ssdhpestage.azurewebsites.net/recommendation.php " 2. Session Expiry has to happen, if kept it for ideal 2 Test Cases - SSDV1.1_099, SSDV1.1_101
21 | Update | Application deployment readiness testing (simulate deployment to production and test)
22 | Regression | Full regression | 78 | 77 | 78 | 1 | Bug ID :- 29
|  | Total | 258 | 257 | 258 | 1
Notes
Testing is not complete yet for the orange zone above
Note on J1: Gomes Narayanan: No new test cases beyond this

## Defects
Defects Count Summary
Severity / Status | Critical | High | Medium | Low | Total
New/Open/Reopen | 0 |  | 1 |  | 1
Fixed |  |  |  |  | 0
Closed | 9 | 20 | 9 | 39 | 77
Total | 9 | 20 | 10 | 39 | 78
ID | Severity | Title | Description | Status | Test Plan ID
29 | Medium | In the Home Page, Search Icon is not there. | In the Home Page, Search Icon is not there. | Reopened
44 | Critical | Performance issues with all sliders taking more than a minute | Critical and showstopper issue | Closed
43 | Medium | Sub-URLs are exposed to end users (naming to be fixed) | Analyze and report the security impact here | Closed
45 | Medium | Performance issues while loading server models in Result page for the 1st time | Query needs to be optimized further | Closed
46 | Medium | Session Expiry has to happen, if kept it for ideal |  | Closed
47 | Medium | In Scalability testing, Response Time and Throughput is not constant, | Prashant needs to fix this | Closed | 18
78 | Medium | In Result Page, SSDs Download Link is redirecting to Homepage | Regression Testing | Closed
19 | High | In the Price Slider, The Max value become Zero and Dollar Sign goes off | In the Refine your Result page, 1.Slightly move the slider towards right side, then dollar sign goes off. 2. Keep the Price Slider as it is, then max price value becomes zero. | Closed | 19
25 | High | In the Results page, Total Number of SSDs meets requirments should be displayed | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the Workloads from the Read, Read/Write and Write Column and click on Next Button 8. Click Next in SSD type 9. Select the Server type as "HPE Moonlight System " and Server Model as "DL 160 Gen10 (Private) and Click "Next" Button 10. In Capacity Page, 0 GB to 10 TB and Click on Next Button 11. In Interface, Select the "SAS", "SATA" and SATAVRO" and Click on Next Button 12. In Capacity Page, Select "M.2 Enablement Kit" and "M.2" and Click on Next Button 13. Results are displayed. | Closed | 19
15 | High | Previous Selected values should show when click on Back Button, it applies for all pages | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the any Workload from the Read Intensive Column and Click on NEXT Button 8. Click on Back Button, | Closed | 19
42 | Critical | All SSDs Compatabilty Servers Results not coming properly based on the Server Type and Server Model | SSDs Compatabilty Servers Results not coming properly based on the Server Type and Server Models such as 1. Appollo Systems Server type and Server Model as "Apollo 4200 Gen10" 2. HPE Synergy Server type and Server Model as "synergy 660 Gen10 " 3. Apollo Systems server type and Server Model as "Apollo 2000 Gen10" 4. HPE Proliant 300 Series Server type and Server Model as "Dl385 Gen 10 Plus" | Closed | 12,13,14,15
1 | Critical | In Refine Your Page, Selected the SSD Type configurations are not showing. | 1.In Workload Page, selected “Database (Mid-Range)” and Click on “Next” 2.In SSD Type Page, by default “Mixed Use”, and I will enable “Very Read Optimized” option and Click on “Next” 3.In the Server Type Page, Choose the Server type from the Drop Down as “HPE ProLiant 500 Series” and Server Model as “Synergy Storage Module” and Click on “Next” 4.In the Capacity Page, Move/Drag the mouse to 500 GB. And Click on “Next” 5.In the Interface Type Page, select for the “SAS and SATA” and Click on “Next” 6.In the Form Factor Page, select for the “3.5 LFF”, “M.2” and “M.2 Enablement Kit” and Click on “Next” 7.In the Last Page click on “Refine Your results” | Closed
2 | Critical | To Verify to, Options are auto selected in the Interface Page based on the previous page configuration | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the any Workload from the Read Intensive Column and Click on NEXT Button 8. Click on "Please select server type" 9. Select the Server type as " HPE Apollo System" 10. Click on Server Model Drop Down 11. Select the DL560 Gen10 12. Click on "Next" Button | Closed
3 | Critical | Results are not shown, When "Select All /I don't know " option selected | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. In the All pages select the "Select All/ I don't know" option and Next Button | Closed
4 | Critical | To Verify to ,All options are selected in SSD type such as Read Intensive Mixed Use Write Intensive | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Click on "Select All/ I don’t know" option 8. Click on Next Button | Closed
5 | Critical | To Verify , Options are auto selected in the Form Factor Page based on the previous page configuration | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the any Workload from the Read Intensive Column and Click on NEXT Button 8. Click on "Please select server type" 9. Select the Server type as " HPE Apollo System" 10. Click on Server Model Drop Down 11. Select the DL560 Gen10 12. Click on "Next" Button 13. Select the Capacity and Click Next Button 14. Select the Options in the interface page | Closed
6 | Critical | The Selected values are not displayed which are selected through “Select All /I Don’t Know” option from the interface and form factor page in the Refine your Results. | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the any Workload from the Read Intensive Column and Click on NEXT Button 8. Click Next Button 9. Select the Sever Type and Server Model and Click Next Button 10. Select the Capacity and Click Next Button 11. In the Interface Page , "Select All /I Don’t Know” option and Click on Next Button 12. In the Form Factor page, "Select All /I Don’t Know” option and Click on Next Button | Closed
7 | Critical | SSDs Results are not displayed, based on the Server type and Model in the Refine your results page and Unable to retrive the previous results also | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the Workloads from the Read, Read/Write and Write Column and click on Next Button 8. Click Next in SSD type 9. Select the Server type as "HPE Moonlight System " and Server Model as "DL 160 Gen10 (Private) and Click "Next" Button 10. In Capacity Page, 0 GB to 10 TB and Click on Next Button 11. In Interface, Select the "SAS", "SATA" and SATAVRO" and Click on Next Button 12. In Capacity Page, Select "M.2 Enablement Kit" and "M.2" and Click on Next Button 13. Results are displayed 10. Click on Refine your results, In the Choose Server type, Select the server as "HPE Apollo Systems" and Server Model as " Apollo 2000 XL170Genr Gen10" 11. Results are not displayed | Closed
8 | High | Next button Working in all pages though it is disabled state | In the all pages , Next button though it is in disabled state, user is abled to click | Closed
9 | High | All target workload shows, though selected workload from "Read " | In the Server Type page, All target workload shows, though selected workload from "Read Performance" column | Closed
10 | High | Validation for the Next Button, Without Choosing a serve model Next gets enabled | In the Server type Page, Without Choosing a serve model Next gets enabled a.Choose the Server type from the Drop Down, b.Then Choose the Server Model from the Drop Down, c.Again, change the Server type from the Drop Down, then don’t Choose the Server Modal from the Drop Down, the Next Button get Enabled. | Closed
11 | High | In “Search By SKU”, Click on Search tab, the page automatically refreshes | In Refine your results page, 1.In “Search By SKU”, Click on Search tab, the page automatically refreshes | Closed
12 | High | Unable to Click on Check Box for Select all applicable checkboxes above. | In Refine your results page, 1.In SSD Type/ Interface type/Form factor/ Certification 2.Click on Any Check Box 3.Then Unable to Check Box 4.Unable to Click on Check Box for Select all applicable checkboxes above | Closed
13 | High | Format of text in all pages are not in uniform. It should have HPE text | In the Server type, Capacity , Interface and Form Factor page | Closed
14 | High | To Verify , Options are in disabled state which are not supporting based on the previous page configuration | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the any Workload from the Read Intensive Column and Click on NEXT Button 8. Click on "Please select server type" 9. Select the Server type as " HPE Apollo System" 10. Click on Server Model Drop Down 11. Select the DL560 Gen10 12. Click on "Next" Button 13. Select the Capacity and Click Next Button | Closed
16 | High | In the Endurance Slider, The Max value become Zero | In the Refine your Result page, 1.Slightly move the slider towards right side, based on the Endurance range results will be displayed. 2. Keep the Endurance Slider as it is, then Endurance max value becomes zero. | Closed
17 | High | Search through SKU key , it is redirecting to home page | In Refine your results page, 1.In “Search By SKU”, Enter the SKU Key and Press Enter | Closed
18 | High | In the Capacity Slider, The Max value become Zero | In the Refine your Result page, 1.Slightly move the slider towards right side, based on the Capacity range results will be displayed. 2. Keep the Capacity Slider as it is, then Capacity max value becomes zero. | Closed
20 | High | In the Max Power Slider, The Max value become Zero | In the Refine your Result page, 1.Slightly move the slider towards right side, then Max Power range will show 2. Keep the Max Power Slider as it is, then Max Power value becomes zero. | Closed
21 | High | In the Capacity page, it shows 0 GB to 480 GB, After sliding it changes to TB | In the Server Type page, 1. Select the Server Type as "HPE Apollo Systems” and Server Model is “DL560 Gen10”, “DL580 Gen10" 2. Click Next Button 3. In the Capacity page, 0 GB to 960 GB 4. Move the mouse from Maximum to minimum or vice versa, it changes to TB Same thing happens for the below server “HPE Integrity “Server Model is DL80 Gen9(EOL) “HPE Moonlight” Server Model is ML150 Gen9(EOL) “HPE ProLiant 300Series Server Model is “Apollo 4500 â€ “XL450 Gen9”, “Apollo 6500 â€ “XL270d Gen10” | Closed
22 | High | In Result Page, Server Type and Server Model are different when it is compared to Server type Page | Click on Refine your results, 1. Click on Server Type as " HPE Apollo System" Server it shows Server as "HPE Proliant 300 Series" | Closed
23 | High | In Capacity Page, The Value of GB/TB should not be able edit . Now It is taking characters |  | Closed
24 | High | In the Server Type page, Without Selecting the Server type and Server Model can be seen by pressing on arrow down | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the Workloads from the Read, Read/Write and Write Column and click on Next Button 8. Click Next in SSD type 9. Select the Server type, Click 10. Press "TAB" twice 11. Then Press arrow key down | Closed | 18
27 | High | Click on Back Button, it is not redirecting to Home Page. | In the Workload page, Click on Back Button, it is not redirecting to Home Page. | Closed
26 | High | Results page URL, copy and paste in another browser, it should redirect to Home page, results not displayed | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the Workloads from the Read, Read/Write and Write Column and click on Next Button 8. Click Next in SSD type 9. Select the Server type as "HPE Moonlight System " and Server Model as "DL 160 Gen10 (Private) and Click "Next" Button 10. In Capacity Page, 0 GB to 10 TB and Click on Next Button 11. In Interface, Select the "SAS", "SATA" and SATAVRO" and Click on Next Button 12. In Capacity Page, Select "M.2 Enablement Kit" and "M.2" and Click on Next Button 13. Results are displayed. 14. Copy the URL results url " https://ssdhpestage.azurewebsites.net/recommendation.php" and paste in another browser | Closed | 18
28 | Medium | When multiple show more are opened then Image disappears when click on show less. | In the SSDs meet your Requirements Page, Click on “Show More” for the multiple SSDs | Closed
30 | Medium | To Verify, Next button is in disabled state when all options are deselected in all pages (WorkLoad/SSD/Server Type/Interface Type/Form Factor Page | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Click on "Select All/ I don’t know" option 8. Again Click on "Select All/ I don’t know" option | Closed
31 | Medium | In Result Page, Price list are not aligined |  | Closed
32 | Medium | if we refresh the page/ click on back button it should redirect to Home Page | In the Workload Page or Server type Page, if we refresh the page it should redirect to Home Page, | Closed | 18
33 | Low | Workloads Options are showing twice | In WorkLoad Page, Workloads Options are showing twice in the Workload Column | Closed
34 | Low | Webpage moves up, when last workload selected from the any column | In Workload Page, Select the last workload from the Read/Mixed/Write Intensive column | Closed
35 | Low | In the Choose Server Page, Page is not loading properly | In the Choose Server Page, Page is not loading properly after refresh it works | Closed
36 | Low | In the Interface type and Form Factor Click on “Select All / I Don’t Know” then selected types of interfaces or Form factors are moving to left side. | In the Interface type and Form Factor Click on “Select All / I Don’t Know” then selected types of interfaces or Form factors are moving to left side. | Closed
37 | Low | In the Server Type and Model Drop Down, Special types characters are showing | In the Server Type and Model Drop Down, Special types characters are showing | Closed
38 | Low | In the Server Type page, Click on “Select All / I Don’t Know” then selected types of Server types and Models are moving to left side. | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Click on "Select All/ I don’t know" option 8. Click on Next Button 9. Click on "Select All/ I don’t know" option in SSD Type 10. Click on Next Button 11. Click on "Select All/ I don’t know" option in Server Type Page | Closed
39 | Low | In the Refine your results page,"Choose Server Model" is not in highlighten mode though server is selected from the drop down | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the Workloads from the Read, Read/Write and Write Column and click on Next Button 8. Click Next in SSD type 9. Select the Server type as "HPE Moonlight System " and Server Model as "DL 160 Gen10 (Private) and Click "Next" Button 10. In Capacity Page, 0 GB to 10 TB and Click on Next Button 11. In Interface, Select the "SAS", "SATA" and SATAVRO" and Click on Next Button 12. In Capacity Page, Select "M.2 Enablement Kit" and "M.2" and Click on Next Button 13. Results are displayed 10. Click on Refine your results, | Closed
40 | Low | In the Interface page, Though "NVMe" is in Lightmode/disabled state, but sub segments are in Highlighten state | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the Workloads from the Read, Read/Write and Write Column and click on Next Button 8. Click Next in SSD type 9. Select the Server type as "HPE Moonlight System " and Server Model as "DL 160 Gen10 (Private) and Click "Next" Button 10. In Capacity Page, 0 GB to 15.3 TB and Click on Next Button 11. In the Interface page, All options are in Light mode/ Disabled state . 12. Click on NVMe , Subsegments are displayed in highlighten mode NVMe Mainstream NVMe High Performance | Closed
41 | Low | To Verify the image content and charcters is Clearly Visible. HPE -Storage Options- SSD Portfolio Alignment Image | 1. Open the Browser 2. Enter the URL and Click on Enter 3. In the "HPE Solid-State Drive Selector Tool" pop up 4. Click on "I Agree" 5. In the SSD Let's get started page 6. Click on "Help me choose" 7. Select the any Workload from the Read Intensive Column and Click on NEXT Button 8. Click on "Please select server type" 9. Select the Server type as "HPE Apollo System" 10. Click on Server Model Drop Down 11. Select the DL560 Gen10 12. Click on Next Button 13. Click on Next Button 14. Click on "Select All / I Don't Know Yet" option 15. Click on Next Button 16. Select the form factor as "M.2" 17. Click on Next Button 18. Click on "Refine Your results" link 19. Click on "SSD Portfoilio Alignment" | Closed
48 | Low | In Workload page, Next button is not enabled, though workload is selected. Then select any other option then Next button get enable. |  | Closed
49 | Low | In Results page, Search Text Moved to right side. |  | Closed
50 | Low | SSD Portfolio Alignment, Image is not displayed. |  | Closed
51 | Low | In Result Page, “Select all applicable checkboxes above” is not working |  | Closed
52 | Low | While Selecting the tool, I selected the Mainstream then also Next is not enabled. | 1.Click on Mainstream Check box, Next Button is enabled 2.Then Click on Non-Mainstream Checkbox, Next Button is enabled 3.Again, Click on Non- Mainstream Checkbox, Next Button gets disabled though Mainstream option is selected | Closed
53 | Low | While selecting the tool, I selected the Non-Mainstream option, In the Results page, it shows Mainstream option selected. In the Results it shows Non-Mainstream |  | Closed
54 | Low | In Results page, After the search, in search tab, remove the SKU key, previous results should retain. But all results are showing |  | Closed
55 | Low | In Results page, “Share” Icon is not highlight |  | Closed
56 | Low | In Results page, click on “Select all applicable checkboxes above” and then All Checkboxes are selected and Again click on “Select all applicable checkboxes above”, then Selected Checkboxes remains as it is. |  | Closed
57 | Low | In Server Model Drop down, please remove the EOL Server Model, because for these Server Models results are not displaying. It should be removed in the Server type page and results page. |  | Closed
58 | Low | When Click on back button in the SSD type page, it redirects to workload page, then in workload page, Next Button is in disabled state, though workload option is selected. |  | Closed
59 | Low | In Server Type page, Server Model changes to last value from the drop down, when click on back Button in the previous pages. | a.Select 1st Value from the drop down, b.Then click Back Button in the Server type page, c.In SSD Type page, Click Back Button d.In Workload Page, select another Workload from the same column which u selected previously then Next button. e.In SSD Type page Click Next Button f.In Server type page, Server Model value shows last value from the drop down | Closed
60 | Low | In Results page, Mainstream and Non-Mainstream checkboxes are not selected then also Results are displayed with Mainstream and Non-Mainstream in SSDs type. | a.Select the Mixed workload and Click Next Button b.Click Next Button c.Select the Server type as “HPE Apollo” and select 1st Server Model and click on Next Button d.Click Next Capacity, Interface, and Form Factor page e.In the Best Availability, Select the Mainstream option, and click Next Button. f.In the Results page 59 SSDS are displayed. The Result is Correct g.Click on Refine your Results link, h.Click on Non-Mainstream Check box, then 105 SSDs are displayed, The Result is Correct i.Then Click on Mainstream and Non-Mainstream Check box. j.Then 203 results are displayed. though Mainstream and Non-Mainstream checkbox are not selected. | Closed
61 | Low | In Results page, initially no image will be shown for all SSDs, when click on Show More option, then image will be displayed for all SSDs, |  | Closed
62 | Low | SSDs Results not coming properly based on the Server Type and Server Model for "HPE Synergy" and Synergy 660 Gen10. |  | Closed
63 | Low | In the SSDs click on Show More, In the Compatibility Server Part, Data base query is showing |  | Closed
64 | Low | Select Edge line Server Type and Model are not displaying. |  | Closed
65 | Low | Select “Apollo Systems/HPE Synergy/HPE ProLiant 10/300/500 Series“ as server type and Select the Server Model “Synergy 660 Gen10” then click Sever Type and select the “Edge line” in the Server Model “Synergy 660 Gen 10“ remains, |  | Closed
66 | Low | Based on the Price Slider results are not showing. Results remain static. And Price Value also changes after sliding Initial value is not retained |  | Closed
67 | Low | In the Server Type page, without selecting the server type and Server Model, Next button is enabled. |  | Closed
68 | Low | In Server type page, two "Proliant Misc Servers “entries are shown please go through it once. |  | Closed
69 | Low | For VRO, Server compatibility is not Showing, It is showing "" like this, |  | Closed
70 | Low | For VRO if Mainstream and Non-Mainstream Checkbox are unchecked, Results are not there. Then also it shows 3. |  | Closed
71 | Low | In Workload page, Wherever Write is there now, please change to Very Read Optimized |  | Closed
72 | Low | In Result Page, it should come “Random WRITE Avg. Latency “ |  | Closed
73 | Low | In the Server type page, for Server type Server Model list is miss matched |  | Closed
74 | Low | Price Slider Maximum Value and SSDs meet your Alignment is not expanding, if Results are “Zero” |  | Closed
75 | Low | If SSDs Results are not there then previous result number remains and link is not expanding. |  | Closed
76 | Low | Then Results are displayed with Mainstream SSDs, though Mainstream option is not selected | In "I Know What I Need", In Result Page, a. Click on Refine Your Results b. Uncheck the Mainstream Checkbox c. Then Select the Very Read Optimized Option -- SSD Type SAS, SATA, NVMe as Interface type 3.5 " LFF, 2.5 "SFF as Form Factor | Closed
77 | Low | Server compatibility is showing "". Loading Icon is needed | 3) In the Result page, Click on Refine Your Results, Click on "Mainstream", a. Select the Server type and Select the "HPE Apollo Systems" and Sever Model as "Apollo 4200", b. then In the SSD, Click on Show more, Server compatibility is showing "". Loading Icon is needed | Closed

## Performance Testing Aug 27th
Pages | Page Loading |  |  | Complete Page Load
Page Navigation | 1st Iteration | 2nd Iteration | 3rd Iteration | 1st Iteration | 2nd Iteration | 3rd Iteration
URL Loading | 4.90 Secs | 3.22 Secs | 1.65 Secs | 6.72 Secs | 4.16 Secs | 2.25 Secs
Home Page Loading | .10 Secs | .10 Secs | .10 Secs | .10 Secs | .10 Secs | .10 Secs
Workload Page Loading | 1.27 Secs | 1.47 Secs | 1.41 Secs | 1.94 Secs | 3.75 Secs | 2.74 Secs
SSD Type Page Loading | 1.24 Secs | 1.75 Secs | 1.51 Secs | 1.70 Secs | 3.37 Secs | 1.90 Secs
Server Type and Model | 1.64 Secs | 1.49 Secs | 4.64 Secs | 1.90 Secs | 2.39 Secs | 5.23 Secs
Capacity Page Loading | 1.87 Secs | 5.67 Secs | 5.59 Secs | 2.13 Secs | 6.69 Secs | 5.59 Secs
Interface Type Page Loading | 1.64 Secs | 2.40 Secs | 3.59 Secs | 2.35 Secs | 4.88 Secs | 6.71 Secs
Form Factor Page Loading | 1.37 Secs | 1.90 Secs | 2.66 Secs | 2.15 Secs | 4.48 Secs | 3.58 Secs
Best Availability | 1.55 Secs | 1.31 Secs | 2.95 Secs | 1.55 Secs | 1.86 Secs | 3.30 Secs
Results | 1.87 Secs | 3.92 Secs | 3.61 Secs | 3.89 Secs | 8.50 Secs | 5.29 Secs
Click on Refine Your Results | 1.27 Secs | 1.12 Secs | 1.13 Secs | 1.20 Secs | 1.12 Secs | 1.13 Secs
Click on Mainstream Checkbox | 1.89 Secs | 4.62 Secs | 1.36 Secs | 1.89 Secs | 4.62 Secs | 1.36 Secs
Click on Mainstream Checkbox | 1.29 Secs | 1.43 Secs | 1.23 Secs | 1.29 Secs | 1.43 Secs | 1.23 Secs
Click on Show More Link | 1.54 Secs | 1.96 Secs | 1.13 Secs | 1.54 Secs | 1.96 Secs | 1.13 Secs
Select the Server Type and Server Model Results displays | 1.99 Secs | 3.20 Secs | 3.54 Secs | 1.99 Secs | 3.20 Secs | 3.54 Secs
Click on "Select all applicable checkboxes above" | 4.24 Secs | 4.07 Secs | 8.30 Secs | 4.24 Secs | 4.07 Secs | 8.30 Secs
Select the Server Type and Server Model Results displays | 1.20 Secs | 3.59 Secs | 6.51 Secs | 1.10 Secs | 3.59 Secs | 6.51 Secs
Select the Different Server Type Server Model List Displays | .10 Secs | .10 Secs | .10 Secs | .10 Secs | .10 Secs | .10 Secs
Capacity Sliding | 3.43 Secs | 2.00 Secs | 3.46 Secs | 3.43 Secs | 2.00 Secs | 3.46 Secs
Capacity Sliding back to Same Position | 4.42 Secs | 3.70 Secs | 1.54 Secs | 4.42 Secs | 3.70 Secs | 1.54 Secs
Price Sliding | 2.12 Secs | 3.31 Secs | 1.24 Secs | 2.12 Secs | 3.31 Secs | 1.24 Secs
Click on Print | 2.50 Secs | 1.41 Secs | 1.23 Secs | 29.06 Secs | 11.08 Secs | 3.15 Secs
Start Over to Home Page Loading | 1.68 Secs | 3.10 Secs | 1.73 Secs | 2.94 Secs | 3.50 Secs | 1.73 Secs

## Scalability Testing Aug 27th
Number of Iterations | Number of Users = N | Ramp Up Time in Secs | Average Respone Time |  | Throughput | Resquest per second | Total Time Taken to Complete | N = ResponeTime*Throughput | Network Usage |  | Memory Usage | Status
|  |  |  | Throughput per user per request |  |  |  |  | Upload Kbps | Download Mbps
1 | 10 | 2 Secs | .412 Secs | 2.13 | 21.3 | 5 Requests | 20 Secs | 8.77 | 384 | 5.5 | 74% | Pass
2 | 15 | 3 Secs | 0.55 | 2.26 | 22.9 | 5 Requests | 34 Secs | 12.595 | 264 | 6.7 | 71% | Pass
3 | 20 | 5 Secs | 1.537 | 0.62 | 12.53 | 4 Requests | 120 Secs | 19.2586 | 512 | 7.7 | 74% | Pass
4 | 25 | 5 Secs | 0.486 | 1.86 | 46.5 | 5 Requests | 150 Secs | 22.59 | 400 | 6.7 | 75% | Pass
5 | 30 | 5 Secs | 0.78 | 1.22 | 36.68 | 6 Requests | 258 Secs | 28.6104 | 425 | 7.7 | 74% | Pass
6 | 35 | 5 Secs | 0.77 | 1.23 | 43.3 | 7 Requests | 255 Secs | 33.341 | 378 | 6.5 | 73% | Pass
7 | 40 | 5 Secs | 0.862 | 1.12 | 44.8 | 8 Requests | 282 Secs | 38.6176 | 400 | 7.7 | 75% | Pass
8 | 45 | 5 Secs | 1.034 | 1.1 | 41.1 | 9 Requests | 344 Secs | 42.4974 | 388 | 6.5 | 74% | Pass
9 | 100 | 60 Secs | 0.552 | 0.59 | 58.77 |  | 90 Secs | 32 | 500 | 7.7 | 70% | Pass
10 | 150 | 60 Secs | 1.425 | 0.4 | 59.77 |  | 134 Secs | 84 | 400 | 6.5 | 68% | Pass
11 | 200 | 60 Secs | 1.068 | 0.45 | 91.81 |  | 124 Secs | 98 | 375 | 6.2 | 68% | Pass
12 | 250 | 60 Secs | 2.29 | 0.28 | 72.1 |  | 184 Secs | 165 | 776 | 12.3 | 69% | Pass
Note
[13 empty] | Average Response Time | 95 Percentile Average response time is 2.3 Secs
[13 empty] | Throughput | 1.3 /Secs

## Performance Testing Aug 26
Pages | Page Loading |  |  | Complete Page Load
Page Navigation | 1st Iteration | 2nd Iteration | 3rd Iteration | 1st Iteration | 2nd Iteration | 3rd Iteration
URL Loading | 4.08 Secs | 1.27 Secs | 1.40 Secs | 6.02 Secs | 1.63 Secs | 1.80 Secs
Home Page Loading | .10 Secs | .10 Secs | .10 Secs | .10 Secs | .10 Secs | .10 Secs
Workload Page Loading | 1.59 Secs | 1.22 Secs | 1.15 Secs | 1.89 Secs | 2.18 Sec | 2.09 Secs
SSD Type Page Loading | .95 Secs | 1.64 Secs | 1.07 Secs | 1.25 Secs | 1.93 Secs | 1.32 Secs
Server Type and Model | .64 Secs | 1.23 Secs | 1.31 Secs | 1.53 Secs | 1.50 Secs | 2.33 Secs
Capacity Page Loading | 1.50 Secs | 1.47 Secs | 1.41 Secs | 2.18 Secs | 2.83 Secs | 2.56 Secs
Interface Type Page Loading | 1.42 Secs | 1.44 Secs | 1.79 Secs | 2.46 Secs | 2.14 Secs | 2.14 Secs
Form Factor Page Loading | 2.05 Secs | 2.12 Secs | 1.44 Secs | 4.26 Secs | 2.65 Secs | 2.11 Secs
Best Availability | 1.23 Secs | 1.09 Secs | 1.38 Secs | 1.51 Secs | 1.55 Secs | 1.38 Secs
Results | 2.61 Secs | 10.42 Secs | 1.75 Secs | 21.06 Secs | 12.76 Secs | 3.48 Secs
Click on Refine Your Results | 1.20 secs | 1.12 Secs | 1.10 Secs | 1.20 Secs | 1.12 Secs | 1.10 Secs
Click on Non-Mainstream Checkbox | 15.65 Secs | 6.87 Secs | 2.33 Secs | 15.68 Secs | 6.87 Secs | 2.33 Secs
Click on Mainstream Checkbox | 2.82 Secs | 2.72 Secs | 2.13 Secs | 2.82 Secs | 2.72 Secs | 2.13 Secs
Click on Show More Link | 1.75 Secs | 1.04 Secs | 1.42 Secs | 1.75 Secs | 1.04 Secs | 1.42 Secs
Click on Mainstream and Non-Mainstream Checkbox | 6.36 Secs | 7.45 Secs | 7.26 Secs | 6.36 Secs | 7.45 Secs | 7.26 Secs
Select the Server Type and Server Model Results displays | 1.99 Secs | 4.57 Secs | 1.97 Secs | 1.99 Secs | 4.57 Secs | 1.97 Secs
Click on "Select all applicable checkboxes above" | 6.19 Secs | 4.91 Secs | 2.85 Secs | 6.19 Secs | 4.91 Secs | 2.85 Secs
Select the Server Type and Server Model Results displays | 2.17 Secs | 1.99 Secs | 3.03 Secs | 2.17 Secs | 1.99 Secs | 3.03 Secs
Select the Different Server Type Server Model List Displays | 8.68 Secs | 4.74 Secs | 1.94 Secs | 8.68 Secs | 4.74 Secs | 1.94 Secs
Select the Server Type and Server Model Results displays | 1.85 Secs | 1.67 Secs | 1.50 Secs | 1.85 Secs | 1.67 Secs | 1.50 Secs
Capacity Sliding | 19.18 Secs | 17.80 Secs | 44.43 Secs | 19.18 Secs | 17.80 Secs | 44.43 Secs
Capacity Sliding back to Same Position | 1:20:00 Secs | 55.61 Secs | 41.20 Secs | 1:20:00 Secs | 55.61 secs | 41.20 Secs
Price Sliding | 42.25 Secs | 45.30 Secs | 1:55:38 Secs | 42.25 Secs | 45.30 Secs | 1:55:38 Secs
Click on Print | 2.53 Secs | 1.96 Secs | 1.87 Secs | 11.20 Secs | 19.88 Secs | 20.56 Secs
Start Over to Home Page Loading | 2.73 Secs | 1.38 Secs | 1.21 Secs | 3.45 Secs | 2.08 Secs | 1.97 Secs

## Scalability Testing Aug 26
Number of Iterations | Number of Users = N | Ramp Up Time in Secs | Average Respone Time |  | Throughput | Resquest per second | Total Time Taken to Complete | N = ResponeTime*Throughput | Network Usage |  | Memory Usage | Status
|  |  |  | Throughput per user per request |  |  |  |  | Upload Kbps | Download Mbps
1 | 10 | 2 Secs | .412 Secs |  | 21.3 | 5 Requests | 20 Secs | 8.77 | 384 | 5.5 | 74% | Pass
2 | 15 | 3 Secs | 0.55 |  | 22.9 | 5 Requests | 34 Secs | 12.595 | 264 | 6.7 | 71% | Pass
3 | 20 | 5 Secs | 0.438 | 2 | 37.3 | 5 Requests | 28 Secs | 16.3374 | 400 | 7.7 | 74% | Fail
4 | 20 | 5 Secs | 0.503 |  | 30.7 | 4 Requests | 34 Secs | 15.4421 | 376 | 6.7 | 73% | Fail
5 | 20 | 6 Secs | 0.504 |  | 30.8 | 3 Request | 34 Secs | 15.5232 | 376 | 6.7 | 73% | Fail
6 | 50 | 5 Secs | 0.583 |  | 66.5 | 10 Request | 40 Secs | 38.7695 | 378 | 6.5 | 73% | Fail
7 | 50 | 40 Secs | 0.495 |  | 42.5 |  | 60 Secs | 21.0375 | 400 | 7.7 | 73% | Fail
8 | 50 | 50 Secs | 0.49 |  | 36.4 | 1 Request | 73 Secs | 18 | 376 | 6.7 | 74% | Fail
9 | 100 | 60 Secs | 0.552 |  | 58.77 |  | 90 Secs | 32 | 500 | 7.7 | 70% | Pass
10 | 150 | 60 Secs | 1.425 |  | 59.77 |  | 134 Secs | 84 | 400 | 6.5 | 68% | Pass
11 | 200 | 60 Secs | 1.068 |  | 91.81 |  | 124 Secs | 98 | 375 | 6.2 | 68% | Pass
12 | 250 | 60 Secs | 2.29 |  | 72.1 |  | 184 Secs | 165 | 776 | 12.3 | 69% | Pass
Note
[13 empty] | Average Response Time | 95 Percentile Average response time is 2.3 Secs
[13 empty] | Throughput | 1.3 /Secs

## Product Backlog
Enhancement
In Result page, After the Selecting the Server type, in the Server Model Tab, "Select Server Model" Label should be seen
In Result page, After selecting the Server type and Server Model, Result page should scroll down to SSDs Result View

## Performace Testing
Pages | Page Loading |  |  | Complete Page Load
Page Navigation | 1st Iteration | 2nd Iteration | 3rd Iteration | 1st Iteration | 2nd Iteration | 3rd Iteration
URL Loading | 6.49 Secs | 1.20 Secs | 1.31 Secs | 8.17 Secs | 1.48 Secs | 1.84 Secs
Home Page Loading | .10 Secs | .10 Secs | .10 Secs | .10Secs | .10 Secs | .10 Secs
Workload Page Loading | 2.96 Secs | 2.16 Secs | 1.65 Secs | 4.03 Secs | 2.50 Secs | 2.15 Secs
SSD Type Page Loading | 1.18 Secs | 1.40 Secs | 1.43 Secs | 1.50 Secs | 1.90 Secs | 1.91 Secs
Server Type and Model | 1.30 Secs | 2.06 Secs | 1.23 Secs | 2.48 Secs | 2.30 Secs | 1.62 Secs
Capacity Page Loading | .98 Secs | 1.20 Secs | 1.87 Secs | 1.28 Secs | 1.20 Secs | 2.27 Secs
Interface Type Page Loading | 1.24 Secs | 1.25 Secs | 1.63Secs | 1.57 Secs | 2.94 Secs | 2.42 Secs
Form Factor Page Loading | 1.63 Secs | 1.12 Secs | 1.33 Secs | 1.91 Secs | 1.93 Secs | 2.08 Secs
Best Availability | 1.08 Secs | 1.46 Secs | 1.46 Secs | 1.38 Secs | 1.46 Secs | 1.69 Secs
Results | 2.01 Secs | 2.66 Secs | 1.40 Secs | 4.67 Secs | 4.07 Secs | 2.20 Secs
Start Over to Home Page Loading | 2.20 Secs | 1.81 Secs | 1.36 Secs | 2.77 Secs | 2.21 Secs | 1.60 Secs

## Scalability Testing
Number of Iterations | Number of Users = N | Ramp Up Time in Secs | Average Respone Time | Throughput | Resquest per second | Total Time Taken to Complete | N = ResponeTime*Throughput | Network Usage |  | Memory Usage | Status
[8 empty] | Upload Kbps | Download Mbps
1 | 10 | 2 Secs | .412 Secs | 21.3 | 5 Requests | 20 Secs | 8.77 | 384 | 5.5 | 74% | Pass
2 | 15 | 3 Secs | 0.55 | 22.9 | 5 Requests | 34 Secs | 12.595 | 264 | 6.7 | 71% | Pass
3 | 20 | 4 Secs | 0.438 | 37.3 | 5 Requests | 28 Secs | 16.3374 | 400 | 7.7 | 74% | Fail
4 | 20 | 5 Secs | 0.503 | 30.7 | 4 Requests | 34 Secs | 15.4421 | 376 | 6.7 | 73% | Fail
5 | 20 | 6 Secs | 0.504 | 30.8 | 3 Request | 34 Secs | 15.5232 | 376 | 6.7 | 73% | Fail
6 | 50 | 5 Secs | 0.583 | 66.5 | 10 Request | 40 Secs | 38.7695 | 378 | 6.5 | 73% | Fail
7 | 50 | 40 Secs | 0.495 | 42.5 |  | 60 Secs | 21.0375 | 400 | 7.7 | 73% | Fail
8 | 50 | 50 Secs | 0.49 | 36.4 | 1 Request | 73 Secs | 18 | 376 | 6.7 | 74% | Fail