## Slide 1: Agile Product Release Grant (PRG) Checkpoint SSD Selector in Azure – v1
(HPE Confidential)
Date: 3/Aug/2020
Document Rev: v1.0
EG Agile PDP
Confidential – EG Agile Release Planning Checkpoint Template v5.0
SIR/PRG
Checkpoint

## Slide 2: Exec Summary
What is the Product/Solution or Release features
SSD Selector v1 with the following features & products
  SSD Selector delivered as SaaS in Azure cloud
  Mainstream SKU Segmentation
  Portfolio alignment update - new swim lanes
  New workload category - Very Read Optimized (VRO)
  New Interface categories – Value SAS and three different sub segments of NVMe.
HPE VGB products in the release scope
  HPE NVMe Mixed Use Solid State Drives
  HPE NVMe Read Intensive Solid State Drives
  HPE SAS Write Intensive Solid State Drives
  HPE SAS Mixed Use Solid State Drives
  HPE SAS Read Intensive Solid State Drives
  Mainstream SKUs
Release Status
Internal QA & Regression cycle – day by day slip (on 8/21)
UAT completed and sign-off – beta released on 8/17
Beta feedback implemented and signed-off
  Feedback on search item
User documentation ready for release – V1 guide released to Lissette
Key Target Dates
ARP checkpoint : 10-Jul-2020
Release (PRG) checkpoint : 21-Aug-2020
CTR/Deploy to Production: 24-Aug-2020
Key Dependencies and Risks
None
Lissette, Gomes

## Slide 3: Development & QA Update

## Slide 4: SSD Selector Prioritized Feature List
EPIC | Story | Feature / Epic Description | FC | QA
E1 | S1 | S1 - Mainstream/ Non-Mainstream |  | 
E1 | S2 | S2 - For the user, provide an option to search SSD by server type, model |  | 
E1 | S3 | S3 - For the user, provide simplified UX experience with minimal clicks and reduced navigations |  | 
E1 | S4 | S4 - For the user, provide output of the tool to be exported in Excel format |  | 
E1 | S5 | S5 - For the user, provide visual representation of the output through graphical representation |  | 
E1 | S6 | S6 - Remove Recommended/Extended as that initiative is no longer being supported. |  | 
E1 | S7 | S7- Update the portfolio alignment slide to add our new swim lanes |  | 
E1 | S8 | S8 - Change the workload categories from 3 to 4 - Very Read Optimized (VRO) |  | 
E1 | S9 | S9 - Update the interfaces categories as well (add Value SAS, add three different sub segments of NVMe, etc.) |  | 
E1 | S10 | S10 - Remove Mezzanine Card from facets |  | 
Copy from features tab in the plan spreadsheet
Completed
On Track
At risk
Not done

## Slide 5: SSD Selector Prioritized Feature List
EPIC | Story | Feature / Epic Description | FC | QA
E2 | S11 | S11 - Implement all SSDs for DL385 Gen10 |  | 
E2 | S12 | S12 - Implement all SSDs for Synergy Gen10 |  | 
E2 | S13 | S13 - Implement all SSDs from Quartz NPI Launch |  | 
E2 | S14 | S14 - Implement all SSDs from Kyanite NPI Launch |  | 
E2 | S15 | S15 - Implement all SSDs for Gen10 Plus Servers |  | 
Copy from features tab in the plan spreadsheet
Completed
On Track
At risk
Not done

## Slide 6: SSD Selector Defect Metrics
Severity  Status | Critical | High | Medium | Low | Total
Closed | 9 | 20 | 9 | 39 | 77
Deferred |  |  |  |  | 
Total | 9 | 20 | 10 | 39 | 77
Severity  Status | Critical | High | Medium | Low | Total
New/Open | 0 | 0 | 1 | 0 | 1
Fixed | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 1 | 0 | 1

## Slide 7: Quality Dashboard – Release Criteria
Category | Overall Status
Integration Test Completeness | 5 Issues completed
Functional Completeness | S12 – S15
Unit Tests | S12 – S15
Defects Containment | 1 Slider perf issue fixed
No regression issues | 
Deployment and update testing for online tools (Deployment to production readiness) | Prashant to test further
Non-Functional [Performance/Scalability] | 
Browser Compatibility Testing | Testing completed
User Documentation | 
Review with Open Source Review Board (OSRB) | N/A
Code Quality & Security | 
Notes: Below are the list of boundaries and equipment constraints that weren’t tested for the code coverage during R&D Development phase.
Synergy / CS750 Solution
  Multiple Logical Enclosure of 3 Frame each --- minimum 6 Frames, upto 21 Frames
  Logical enclosure comprising 2 - 5-Frame
CS700
  VMware 6.7 version
  CS700 setup with May 2019 recipe
Release notes open for any late breaking information. On approval, this will turn blue.

## Slide 8: SSD Selector – Test Metrics
Module / | # of Test cases | Passed | Failed | Not Run | Blocked | Remarks
Component / Category / Subsystem |  |  |  |  |  | 
SSD Selector Tool Features Test Cases - Category1 (Homepage, Workload, SSD type, SSD Server Type and Capacity) | 46 | 45 | 1 |  |  | Search Icon in Home Page
SSD Selector Tool Features Test Cases – Category2 (Interface, Form Factor and Mainstream) | 23 | 23 | 0 |  |  | 
SSD Selector Tool Features Test Cases – Category3 (Results) | 36 | 36 | 0 |  |  | 
SSD Product Coverage Test Cases – Synergy Gen10 | 6 | 6 | 0 |  |  | 
SSD Product Coverage Test Cases – NPIs Launches (Kynaite, Quartz) | 12 | 12 | 0 |  |  | 
SSD Product Coverage Test Cases – All Gen10+ Servers, DL385 Gen10 | 6 | 6 | 0 |  |  | 
Application Performance and Scaling | 22 | 22 | 0 |  |  | 
Regression Test Cases | 78 | 77 | 1 |  |  | In the Home Page, Search Icon is not there.

## Slide 9: SSD Selector OPEN Defects List
ID | Severity | Summary | Status
SSDV1.1_159 | Medium | In the Home Page, Search Icon is not there. | Open

## Slide 10: SSD Selector Deferred Defects List
Jira ID | Summary | Severity | Impact/Justification | Workaround | Proposal

## Slide 11: Core Team & Stakeholder approval
Name | Role | PRG Signoff Date : 21/Aug/2020
Lissette Cruz | Product Management | 
Nathalie | Marketing | 
Gomes | Program Management | 

## Slide 12: Backup

## Slide 13: CI/CD – Metrics
 | Feature Set1 | Feature Set2 | Product Set1
# CI/CD cycles |  |  | 1
# Epic * |  |  | 1
# Stories** |  |  | 16
Automated Tests Overhead (hrs) |  |  | 2
Manual Tests Overhead (hrs) |  |  | 20
Features and EPICs & Stories delivered through this CI/CD release
Notes:
* includes fully completed EPICs only
** Stories that are part of partially completed EPICs
Notes: SCID
May 13: Refinitiv order fixes
May 28: SAP HANA
May 20: PI-3